## Document Control
User Acceptance Test Scripts - Fleet Management
Document reference: | UAT_Fleet_Management
Generated on: | 2026-03-03
Template style: | User Acceptance Test Scripts – Fleet Management (PDF)

## Model Test Scripts
Test Case ID | Model Name | Feature | Test Case Title / Description | Test Steps | Expected Result | Actual Result (Pass/Fail) | Comment / Note
FLT-MDL-01 | fleet.vehicle.request | Vehicle Request | Create vehicle request in Draft | 1. Open Fleet Operations > Vehicle Requests. 2. Click New. 3. Capture requester, purpose, start/end datetime, passenger count. 4. Save. | Sequence is generated for Request; state remains Draft; record is saved successfully.
FLT-MDL-02 | fleet.vehicle.request | Vehicle Request | Submit request for approval | 1. Open a Draft vehicle request with valid dates. 2. Click Submit. | State changes from Draft to Submitted.
FLT-MDL-03 | fleet.vehicle.request | Vehicle Request | Validate date constraint on request | 1. Create/edit request where End datetime is earlier than Start datetime. 2. Attempt to save or submit. | Validation error is shown: End time must be after start time.
FLT-MDL-04 | fleet.vehicle.request | Vehicle Request | Approve and allocate request | 1. As manager click Manager Approve. 2. As fleet office click Fleet Approve. 3. Set Vehicle and Driver. 4. Click Allocate. | State changes to Allocated; Trip Log and Key Register records are auto-created and linked.
FLT-MDL-05 | fleet.vehicle.request | Vehicle Request | Complete allocated request | 1. Open Allocated request. 2. Click Complete. | State changes to Completed; trip end time is populated when missing; open key register is returned.
FLT-MDL-06 | fleet.after.hours.authorization | After-Hours Authorization | Create and submit after-hours authorization | 1. Open Fleet Operations > After-Hours Authorizations. 2. Click New and enter start/end datetime and reason. 3. Click Submit. | Authorization number is generated; state changes to Submitted.
FLT-MDL-07 | fleet.after.hours.authorization | After-Hours Authorization | Run two-step approval for after-hours authorization | 1. Open Submitted authorization. 2. Click Manager Approve. 3. Click Fleet Approve. | State transitions to Manager Approved then Fleet Office Approved; approver users are recorded.
FLT-MDL-08 | inspection.request | Inspection Request | Create inspection request and confirm | 1. Open Vehicle Inspections > Inspection Requests. 2. Create request with Inspection template, Vehicle, Inspection Date. 3. Click Confirm Inspection. | State changes to New; linked Inspection Request Line is created if not present.
FLT-MDL-09 | inspection.request | Inspection Request | Run inspection lifecycle | 1. Open New inspection request. 2. Click Start Inspection. 3. Capture checklist outcomes/images. 4. Click Finish Inspection. | State changes from New to Inspection Started to Inspection Finished.
FLT-MDL-10 | inspection.request | Inspection Request | Create linked service from inspection | 1. Open inspection request. 2. Click Create Service. | Service wizard/record opens with inspection, vehicle, and odometer defaults; service reference is stored.
FLT-MDL-11 | inspection.request.line | Inspection Schedule Line | Maintain inspection schedule line | 1. Open Inspection Request Lines. 2. Create line with vehicle and inspection reference. 3. Set next inspection date. | Line stores inspection period/reminder from template and remains available for reminder automation.
FLT-MDL-12 | vehicle.inspection | Inspection Template | Create inspection template | 1. Open Vehicle Inspection templates. 2. Click New. 3. Enter name, period (days), reminder days, supervisor. 4. Save. | Inspection template is saved and reusable in inspection requests.
FLT-MDL-13 | inspection.images | Inspection Images | Attach images to inspection | 1. Open inspection request. 2. Add image entries under inspection images. 3. Save. | Images are stored and linked to inspection request; available for reporting.
FLT-MDL-14 | fleet.vehicle.key.register | Vehicle Key Register | Create key register entry | 1. Open Key Register. 2. Create entry with vehicle, key number, issued to, issue datetime. 3. Save. | Key register sequence is generated; state defaults to Out.
FLT-MDL-15 | fleet.vehicle.key.register | Vehicle Key Register | Return issued key | 1. Open key register entry in Out state. 2. Click Return. | State changes to Returned and Returned On datetime is auto-populated.
FLT-MDL-16 | fleet.vehicle.key.register | Vehicle Key Register | Prevent duplicate active key issue | 1. Keep one Out entry for same vehicle + key number. 2. Attempt creating second Out entry with same combination. | Validation prevents duplicate open key issue for same vehicle/key.
FLT-MDL-17 | fleet.vehicle.trip.log | Trip Log | Capture trip logbook entry | 1. Open Trip Log. 2. Create entry with vehicle, driver, start/end, destination, odometer values. 3. Save. | Trip log sequence is generated; record is linked to request when provided.
FLT-MDL-18 | fleet.vehicle.daily.checklist | Daily Vehicle Checklist | Capture daily checklist | 1. Open Daily Checklist. 2. Create record with date, vehicle, driver, odometer and checklist answers. 3. Save. | Checklist sequence is generated; checklist is stored and linked to request when provided.
FLT-MDL-19 | fleet.vehicle.accident.report | Accident Report | Log accident report | 1. Open Accident Reports. 2. Create report with accident date, vehicle, location and description. 3. Save. | Accident report sequence is generated; full insurance/claim fields are available for capture.
FLT-MDL-20 | fleet.fuel.register | Fuel Register | Create monthly fuel register | 1. Open Fuel Register. 2. Create register with month, year, depot. 3. Save. | Fuel register sequence is generated and ready for fuel line entries.
FLT-MDL-21 | fleet.fuel.register.line | Fuel Register Line | Add fuel consumption line item | 1. Open a fuel register. 2. Add line with date, vehicle, driver, opening/closing odometer, liters and value. 3. Save. | Fuel line is saved under the selected register with monetary currency from company.
FLT-MDL-22 | fleet.job.card | Job Card | Capture job card | 1. Open Job Cards. 2. Create card with vehicle/driver, work description, kms and service feedback. 3. Save. | Job card sequence is generated; signatures can be attached.
FLT-MDL-23 | fleet.policy.document | Policy Document | Create policy document | 1. Open Policy Documents. 2. Create policy with type, effective date, summary and attachments. 3. Save. | Policy sequence is generated; document is available for audit/reference.
FLT-MDL-24 | fleet.vehicle.service.logbook | Service Logbook | Create service logbook entry | 1. Open Service Logbook. 2. Create entry with vehicle, date, opening/closing odometer and service details. 3. Save. | Service logbook sequence is generated and record is stored.
FLT-MDL-25 | vehicle.service.log | Vehicle Service Log | Maintain detailed service log from inspection | 1. Open service log linked from inspection. 2. Add inspection result, internal notes, images, and additional services. 3. Save. | Service log retains inspection-specific media and service references.
FLT-MDL-26 | fleet.sub.service.type | Sub Service Type | Create sub service type | 1. Open Sub Service Types. 2. Create record and select Service Type. 3. Save. | Service Category is auto-populated from selected Service Type category.

## Process Flow Scripts
Test Case ID | Feature | Test Case Title / Description | Test Steps | Expected Result | Actual Result (Pass/Fail) | Comment / Note
FLT-FLW-01 | Transport Request End-to-End | Request to completion lifecycle | 1. Create Vehicle Request (Draft). 2. Submit > Manager Approve > Fleet Approve. 3. Allocate vehicle + driver. 4. Complete request after trip. | Lifecycle reaches Completed; system auto-creates Trip Log and Key Register then returns key on completion.
FLT-FLW-02 | After-Hours Linked Authorization | Use after-hours approval before transport | 1. Create and approve After-Hours Authorization. 2. Create Vehicle Request and link authorization. 3. Submit and approve request. | Both workflows are auditable with approver trail and linked records.
FLT-FLW-03 | Inspection Reminder to Service | Scheduled inspection and service follow-through | 1. Create Vehicle Inspection template and Inspection Request Line. 2. Run scheduled reminder job/date condition. 3. Open auto-created Inspection Request and complete inspection. 4. Create service from inspection. | Inspection request is generated from schedule; inspection completes; service record is created with carried defaults.
FLT-FLW-04 | Operational Daily Control | Daily checklist + key + trip + fuel records coherence | 1. Allocate vehicle request. 2. Create daily checklist. 3. Capture trip log and fuel register line for same vehicle/day. 4. Complete request. | Operational records exist and can be cross-referenced by vehicle/request/date.
FLT-FLW-05 | Incident to Insurance Traceability | Capture accident with claim information | 1. Log accident report with core incident details. 2. Update insurance/claim/survey fields. 3. Attach evidence files and signatures. | Single accident report contains complete traceability from incident capture to insurance handling.

## Open_Closed_Issues
ID | Issue | Resolution | Responsibility | Target Date | Impact Date | Status
Open Issues
Closed Issues